## Electrical
Standard Formula for Electrical Machinery - Home
| REF | SYMBOL | DEFINTIONS | VALUES
P1 = P0 ( 0.05 + 0.475*M1/M0 + 0.475*L1/L0 )
M E T H O D - 1 | A | P0 | Contract Price | 20000
| B |  | Tender or Cost Basis Date | 2005-01-20
| C |  | Date of Order | 2005-02-14
| D |  | Date when ready for depatch or taking over | 2008-08-12
| E |  | Contract Period in days between C and D | 1275
| F |  | Date at 1/3 of Contract Period (1/3*1275 =425 days) from C | 2006-04-15
| G |  | Date at 2/5 of Contract Period (2/5*1275 = 510 days) from C | 2006-07-09
| H |  | Date at 4/5 of Contract Period (4/5*1275 = 1020 days) from C | 2007-12-01
| I | L0 | Labour cost Index (Electrical 1980=100) at Tender or Cost Basis Date (B) | 640.2
| J | L1 | Average of Beama Labour Cost Indices (Electrical 1980=100) for the Period of F to D (Please refer to Electrical-Indices sheet) | 702.0552
| K | M0 | Materials Index for Basic Electrical Equipment (2000=100) last published before Tender or Cost Basis Date | 113.3
| L | M1 | Average of the Materials Indices for Basic Electrical Equipment (2000=100) commencing with Index last published before date at G and ending with the index last published at H (Please refer to Electrical-Indices sheet) | 135.8684
| M |  | % Labour adjustment 47.5*(L1-L0)/L0 | 4.5894
| N |  | % Material adjustment 47.5*(M1-M0)/M0 | 9.4616
| O |  | Total % Adjustment for Labour and Materials (M + N) | 14.051
| P |  | Adjusted Contract Price (O% of A) | 2810.1972
|  | P1 | Final Contract Price (P + A) | 22810.1972
M E T H O D - 2 |  | SYMBOL | DEFINTIONS | VALUES
|  | P0 | Contract Price | 20000
|  | M1 | Average Material Cost Index (Electrical) (Please refer to Electrical-Indices sheet) | 135.8684
|  | M0 | Initial Material Index (Electrical) | 113.3
|  | L1 | Average Labour Cost Index (Electrical) (Please refer to Electrical-Indices sheet) | 702.0552
|  | L0 | Initial Labour Cost Index (Electrical) | 640.2
|  | P1 | Final Contract Price = P0 ( 0.05 + 0.475*M1/M0+0.475*L1/L0 ) | 22810.1972
Formulas:
VALUES = 1/3*[VALUES, row above]+E6

## Electrical-Indices
LABOUR (ELECTRICAL 1980=100) |  |  | MATERIALS (ELECTRICAL 2000=100)
Average of Beama Labour Cost Indices for the Period at 1/3 of the (Contract Period) to the date when ready for depatch or taking over |  |  | Average of BEAMA Index figures of Materials commencing with Index last published before date at 2/5 of (Contract Periord) and ending with the index last published at 4/5 of (Contract Period)
2005 | JAN | 640.2 | 2005 | 18th Jan’05 | 113.3
2006 | APR | 666.7 | 2006 | 16th May | 136.1
| MAY | 668.1 |  | 20th Jun | 134.9
| JUN | 670.8 |  | 18th Jul | 133.4
| JUL | 672.8 |  | 22nd Aug | 136.1
| AUG | 673.5 |  | 19th Sep | 136
| SEP | 674.2 |  | 17th Oct | 132.7
| OCT | 676.2 |  | 21st Nov | 135.4
| NOV | 678.3 |  | 19th Dec | 140.4
| DEC | 685.9 | 2007 | 23rd Jan’07 | 141.3
2007 | JAN | 694.3 |  | 20th Feb | 137.9
| FEB | 696.3 |  | 20th Mar | 136.7
| MAR | 694.6 |  | 24th Apr | 136.5
| APR | 693.2 |  | 22nd May | 132.7
| MAY | 701 |  | 19th Jun | 133.5
| JUN | 708.1 |  | 17th Jul | 134
| JUL | 713.2 |  | 21st Aug | 134.4
| AUG | 713.8 |  | 18th Sep | 134.5
| SEP | 716.8 |  | 16th Oct | 135.7
| OCT | 717.5 |  | 20th Nov | 139.3
| NOV | 718.2 |  | M1 | 135.8684
| DEC | 718.2
2008 | JAN | 721.1
| FEB | 726.3
| MAR | 724.3
| APR | 722
| MAY | 721.3
| JUN | 725.7
| JUL | 732.3
| AUG | 734.9
| L1 | 702.0552